## Example
[Funding Program Name]
Program/project title: | [Enter title here]
Lead PI(s): | [enter name(s)]
Application type: | [CTP: CATA/Pre-CATA; AO: Project/Program/Resource/Network; CTIP: EA/LA/LG]
Funding term: | [enter term here]
Original Deliverables and Milestones (D/Ms) at the time of application |  |  |  |  | Update 1: April 2022 |  |  | Update 2: April 2023
[5 empty] | On track, Delayed (<2Q), Delayed (>2Q), On hold, Terminated |  |  | On track, Delayed (<2Q), Delayed (>2Q), On hold, Terminated
Deliverable | Original deliverable timing | Milestone | Original milestone timing | Comments | Updated deliverable timing | Updated milestone timing | Comments | Updated deliverable timing | Updated milestone timing | Comments
Deliverable 1: description | Q3, FY2024-25 | Milestone 1.1: description | Q1, FY2022-23 |  | Q3, FY2024-25 | On hold | Delays in hiring | Q2, FY2025-26 | ACHIEVED - Q3, FY2022-23 | Individual was hired and milestone was achieved 2 quarters later than originally projected.
|  | Milestone 1.2: description | Q3, FY2022-23 |  |  | Q4, FY2022/23 | Equipment requires repair |  | ACHIEVED - Q4, FY2022-23 | Equipment was successfully repaired and milestone was achieved one quarter later than anticipated.
|  | Milestone 1.3: description | Q2, FY2023-24 |  |  | Q2, FY2023-24 |  |  | Q4, FY2023-24 | Delays in acessing samples
|  | Milestone 1.4: description | Q3, FY2024-25 |  |  | Q3, FY2024-25 |  |  | Q2, FY2025-26 | Delays in accessing samples which will further delay analysis
Deliverable 2: description | Q4, FY2024-25 | Milestone 2.1: description | Q1, FY2024-25 |  | Q3, FY2025-26 | Q1, FY2024-25 |  | Q3, FY2025-26 | Q1, FY2024-25
|  | Milestone 2.2: description | Q4, FY2024-25 |  |  | Q3, FY2025-26 | Delays in accessing samples for analysis |  | Q3, FY2025-26 | Delays persisting in sample acquisition
OICR Fiscal Year (FY)
Q1: April 1 - June 30
Q2: July 1 - September 30
Q3: October 1 - December 31
Q4: January 1 - March 31
MOVE THIS BOX TO SEE THE EXAMPLES IN THE TABLE BEHIND AFTER READING
This worksheet ('Example') shows how Deliverables and Milestones (D/M) are to be organized when preparing the D/M upload for a new funding application. Use the next tab ('Deliverables & Milestones') to draft your D/Ms for the application.
Information in the box outlined in GREEN (columns A-E) shows an example of how to draft D/Ms for your application. If your application is selected for funding you will then use the columns outlined in BLUE (columns F-K and beyond as necessary) to submit progress updates.
Application (columns A-E):
Provide a list of deliverables and the expected date the deliverable will be achieved in columns A and B. Then, provide associated milestones and the dates for milestone achievement in columns C and D. You may use the 'Comments' (column E) if there is something you would like to include, but this is not required. This is all that is required at the application stage.
Progress updates (if selected for funding):
Please note that these columns are HIDDEN on the 'Deliverables and Milestones' tab as they are not required at the application stage. If your proposal is selected for funding, they can be un-hidden to complete your progress updates. They should remain blank and hidden when you submit your initial application.
Referring to the D/Ms you provided at the time of application (columns A-E) provide a status update on all deliverables and milestones. The 'Updated deliverable/milestone timing' should be a current estimate of when the deliverable and milestones are expected to be achieved. This may be the same as what was provided at the time of application or revised. Use the colour-coding scheme to indicate if the item is On track, ACHIEVED, Delayed (<2Q), Delayed (>2Q), On hold, or Terminated. All updates should be compared the 'original' timing that was provided at the time of application and NOT compared to updated timing provided in previous progress updates.
If you need to add new Deliverables and/or Milestones during the progress update you may add rows as necessary and indicate the deliverable/milestone as *NEW*.

## Deliverables & Milestones
Cancer Pathology Translational Research Grant (CPTRG)
Program/project title: | [Enter title here]
Lead PI(s): | [enter name(s)]
Application type: | OMPRN: CPTRG Project
Funding term: | March 1, 2026 - February 28, 2027
Original Deliverables and Milestones (D/Ms) at the time of application |  |  |  |  | Update 1: [date] |  |  | Update 2: [date] |  |  | Update 3: [date] |  |  | Update 4: [date] |  |  | Update 5: [date] |  |  | Update 6: [date]
[5 empty] | On track, Delayed (<2Q), Delayed (>2Q), On hold, Terminated |  |  | On track, Delayed (<2Q), Delayed (>2Q), On hold, Terminated |  |  | On track, Delayed (<2Q), Delayed (>2Q), On hold, Terminated |  |  | On track, Delayed (<2Q), Delayed (>2Q), On hold, Terminated |  |  | On track, Delayed (<2Q), Delayed (>2Q), On hold, Terminated |  |  | On track, Delayed (<2Q), Delayed (>2Q), On hold, Terminated
Deliverable | Original deliverable timing e.g., Q4 2026-27 | Milestone | Original milestone timing e.g., Q4 2026-27 | Comments | Updated deliverable timing | Updated milestone timing | Comments | Updated deliverable timing | Updated milestone timing | Comments | Updated deliverable timing | Updated milestone timing | Comments | Updated deliverable timing | Updated milestone timing | Comments | Updated deliverable timing | Updated milestone timing | Comments | Updated deliverable timing | Updated milestone timing | Comments
Deliverable 1: description | [Deliverable timing] | M1.1: description | [Milestone timing]
|  | M1.2: description | [Milestone timing]
Deliverable 2: description | [Deliverable timing] | M2.1: description | [Milestone timing]
|  | M2.2: description | [Milestone timing]
Deliverable n: description | [Deliverable timing] | Mn.1: description | [Milestone timing]
|  | Mn.2: description | [Milestone timing]
OICR Fiscal Year (FY)
Q1: Apr 1 - Jun 30
Q2: Jul 1 - Sept 30
Q3: Oct 1 - Dec 31
Q4: Jan 1 - Mar 31